## Sheet1
Week | Task | Estiamation (Story Points)
2022-10-01 | preparation including github | 1
2022-10-08 | Configure a cloud shell including access | 2
2022-10-15 | Set up project Into Azure Cloud Shell | 1
2022-10-22 | creation of necessary files | 1
2022-10-29 | set up GitHub Actions | 2
2022-11-05 | configure Azure Pipelines | 5
2022-11-12 | test continuoues delivery | 5
2022-11-19 | project Documentation | 2
2022-11-26 | QA | 5
2022-12-03 | System Demo | 2
Goals
Configure GitHub Actions for CI
Configure Azure Pipelines integration for CD
Build up Application Code on Top of Project Scaffolding
Presentation of a working application